## PUNCH LIST
Item | Created Date | Resolved Date | Notes
Add support for migrating only active assets | 2013-05-13 |  | migrateClosedAssets = false
PROJECTS: All projects that were assigned to scope:0 should be in target project | 2013-05-24 | 2013-05-31
Add support for synchronizing standard list type values. | 2013-05-24 | 2013-06-03 | EX: Priority, Category, etc.
Add "Previous VersionOne ID" field to all assets that have V1 "Numbers" | 2013-05-24 | 2013-06-06
Add "(V1 #####)" to title of backlog items on import | 2013-05-24 | 2013-06-04 | Implmented for all assets containing a V1 "number". (EX: D-12345)
Add support for setting the source project to export (include sub-projects) | 2013-05-24 | 2013-05-31
Create single process for closing all assets | 2013-05-24 | 2013-06-04 | Should occur at the very end of the import.
Need to preserve asset rank on import | 2013-05-25 | 2013-06-03 | Preserved within asset type.
Ensure that import process for all assets checks for required fields | 2013-05-25
Add ability to configure export paging | 2013-06-03 | 2013-06-04
DEFECT: Add Versions (VersionLabel)? | 2013-06-04 | 2013-06-04 | Will not implement, attribute is no longer used.
Refactor story/defect template migration | 2013-06-04 |  | Should account for templates on import, not delete them from staging database.
Trim uneccessary fields from V1Migration database | 2013-06-04 |  | Mainly relationship fields since the relationships are only handled with certain assets and not others.
Add config option for importing project membership | 2013-06-04 | 2013-06-04
Ensure that only one attachment is exported at a time | 2013-06-04 |  | Paging = 1; do this to try and avoid timeout issues.
Add ability to handle data transformations per asset field | 2013-06-03
Add count of duplicates found to import results | 2013-06-10 |  | Ensure that duplicates are not part of regualr count totals
Refector duplicate checking | 2013-06-12 |  | Reduce arguments for IImportAssets.CheckForDuplicateInV1 method.
Record source V1 version in staging db | 2013-06-14 |  | Needed for when customer run the export themselves
FIX: Import of listtypes for source versions | 2013-06-14 |  | Issue with listype conversions for epics (see import listtypes class)
Need to synchronize custom list types | 2013-06-14 |  | Right now we assume that target contains the correct values and use API to lookup. Need to lookup from DB.

## WISH LIST
Item | Created Date | Requested By | Notes
Add auto-discovery for source/target components | 2013-05-13 | Acey
Change export DB to SQLCompact | 2013-05-13 | Acey
Move configurations out of config file | 2013-05-13 | Acey
Add export/import of restospectives | 2013-05-24 | Acey
Need to preserve rank for blended backlog items (stories and defects) | 2013-06-03 | Acey
Build wizard interface for migration tool | 2013-05-13 | Acey
Add export support for V1 version 12 | 2013-05-13 | Acey
Add export support for V1 version 10 | 2013-05-13 | Acey
MEMBERS: Add support for export/import of avatars | 2013-05-21 | Acey
Add import status = "IMPORTED¦FAILED" to new field in migration DB | 2013-05-24 | Acey
Add ability to store data loss - items that could not be migrated | 2013-05-23 | Acey | Example: Orphaned items like and iteration based on a schedule that has been deleted.
Add export/import error field to all tables in migration DB | 2013-05-24 | Acey
Improve export/import reporting results | 2013-06-03 | Acey | Number imported, number failed, and why.
Add ability to limit which assets get imported | 2013-06-03 | Acey | EX: Specific schedules, by createDate, etc.
If a timeout occurs, remember state and try to reconnect and continue | 2013-06-04 | Acey | Goes above and beyond paging for exports. This would be for both export and import.
Migrate workspace configuration | 2013-06-06 | Acey
Generate migration report | 2013-06-06 | Acey | Report would include metric for export/import/closing, successes and failures.
Add config otion for setting the duplicate field check | 2013-06-10 | Acey | For example, for members dups could be checked on name, username, or email address.
EXPORT: Should not export attachments with no associated asset | 2013-06-14
EXPORT: Should not export links with no associated asset | 2013-06-14
Add "Previous V1 Create Date" to all imported assets | 2013-06-14 |  | Similar to "Previous V1 ID", will show the date that the asset was created in the old system.

## ASSET METRICS
Asset | Derived Type | Has Scope? | Has Links/Attach? | Has Conversations? | Rankable? | Closeable? | Uses Number? | Custom V1 ID? | Notes
ListTypes | N/A | NO | NO | NO | NO | YES | NO | NO | Is actually rankable but ignoring rank for now.
Members | BaseAsset | NO | YES | YES | N/A | YES | NO | NO
MemberGroups | Label | NO | NO | NO | N/A | NO | NO | NO
Teams | BaseAsset | NO | YES | YES | N/A | YES | NO | NO
Schedules | BaseAsset | NO | YES | YES | N/A | YES | NO | NO
Projects | BaseAsset | YES | YES | YES | N/A | YES | NO | NO
Programs | Workitem | NO | NO | YES | N/A | NO | NO | NO
Iterations | BaseAsset | NO | YES | YES | N/A | YES | NO | NO | Uses "Close" operation to close (not "Inactivate").
Goals | BaseAsset | YES | YES | YES | N/A | YES | YES | NO | Cannot add custom field?
FeatureGroups | Label | YES | YES | YES | YES | YES | YES | YES
Requests | BaseAsset | YES | YES | YES | YES | YES | YES | YES
Issues | BaseAsset | YES | YES | YES | YES | YES | YES | YES
Epics | Workitem | YES | YES | YES | YES | YES | YES | YES
Stories | PrimaryWorkitem | YES | YES | YES | YES | YES | YES | YES
Defects | PrimaryWorkitem | YES | YES | YES | YES | YES | YES | YES
Tasks | Workitem | NO | YES | YES | YES | YES | YES | YES | Scope is inherited from parent (PrimaryWorkitem).
Tests | Workitem | NO | YES | YES | YES | YES | YES | YES | Scope is inherited from parent (PrimaryWorkitem).
Links | N/A | NO | NO | NO | N/A | NO | NO | NO | Scope is inherited from asset (BaseAsset).
Attachments | N/A | NO | NO | NO | N/A | NO | NO | NO | Scope is inherited from asset (BaseAsset).
Conversations | N/A | NO | NO | YES | N/A | NO | NO | NO
Actuals | N/A | YES | NO | NO | N/A | NO | NO | NO

## LIST TYPES
Asset | Name | Internal Name | Notes
Members | N/A
MemberGroups | N/A
Teams | N/A
Schedules | N/A
Projects | Status | ScopeStatus
Programs | N/A
Iterations | N/A
Goals | Priority | GoalPriority
| Category | GoalCategory
FeatureGroups | Status | ThemeStatus
| Category | ThemeCategory
| Source | ThemeSource
| Risk | WorkitemRisk
| Priority | WorkitemPriority
| Area | ThemeLabel
Requests | Resolution Reason | RequestResolution
| Source | StorySource
| Priority | RequestPriority
| Status | RequestStatus
| Category | RequestCategory
Issues | Resolution Reason | IssueResolution
| Category | IssueCategory
| Source | StorySource
| Priority | IssuePriority
Epics | Category | EpicCategory
| Source | StorySource
| Priority | EpicPriority
| Status | EpicStatus
Stories | Risk | WorkitemRisk
| Source | StorySource
| Priority | WorkitemPriority
| Status | StoryStatus
| Category | StoryCategory
Defects | Versions | VersionLabel | No longer used in V1, will not migrate.
| Type | DefectType
| Resolution Reason | DefectResolution
| Source | StorySource
| Priority | WorkitemPriority
| Status | StoryStatus
Tasks | Category | TaskCategory
| Source | TaskSource
| Status | TaskStatus
Tests | Status | TestStatus
| Category | TestCategory
Links | N/A
Conversations | N/A
Actuals | N/A
Attachments | Category | AttachmentCategory